# Communication Protocols

# Baie Verte Economic Development Project

Project:e Verte Economic Development Plan for Firefly Metals Mining Expansion

Version:

Date Created:uary 2025

Last Updated:uary 2025

Owner:ject Management Team

Review Period:rterly or as needed

# Document Purpose

This document establishes comprehensive communication protocols for the Baie Verte Economic Development Project. These protocols ensure consistent, timely, and effective communication across all stakeholders, project team members, and working groups throughout Phase 1 and subsequent phases.

Objectives:

- Ensure all stakeholders receive appropriate information at the right time

- Maintain transparency and build trust through consistent communication

- Facilitate efficient decision-making through clear communication channels

- Document all key communications for project records

- Support stakeholder engagement and alignment

# Communication Principles

## Core Principles

- Transparency:n and honest communication with all stakeholders

- Timeliness:ormation shared at appropriate times to support decision-making

- Clarity:ar, concise, and jargon-free communication

- Consistency:ndardized formats and processes across all communications

- Accessibility:ormation accessible to all stakeholders regardless of technical background

- Accountability:ar ownership and responsibility for communications

- Confidentiality:ropriate handling of sensitive information

## Communication Standards

- Professional Tone: communications maintain professional, respectful tone

- Cultural Sensitivity:pectful of Indigenous communities and cultural protocols

- Bilingual Consideration:ommodate English and French as needed

- Plain Language:id technical jargon; explain when necessary

- Action-Oriented:munications include clear next steps and responsibilities

# Stakeholder Communication Matrix

## Communication Channels by Stakeholder Group

| Stakeholder Group | Primary Channel | Frequency | Format | Owner |
| --- | --- | --- | --- | --- |
| ------------------ | ---------------- | ----------- | -------- | ------- |
| Steering Committee | Formal meetings + email | Bi-weekly | Executive summary, decision briefs | Project Manager |
| Town Council | Council meetings + reports | Monthly | Progress reports, decision requests | CAO |
| Firefly Metals | Meetings + email | Bi-weekly | Status updates, requirement confirmations | Project Manager |
| Working Groups | Meetings + shared workspace | Weekly | Work plans, status updates | Working Group Leads |
| Project Team | Team meetings + collaboration tools | Weekly | Task updates, blockers, decisions | Project Manager |
| Local Businesses | Information sessions + email | Monthly | Opportunity updates, engagement invitations | Stakeholder Coordinator |
| Qalipu First Nation | Consultation meetings | As required | Consultation materials, updates | Stakeholder Coordinator |
| Provincial Government | Meetings + formal reports | Monthly | Progress reports, funding updates | Project Manager |
| Federal Government | Meetings + formal reports | Quarterly | Comprehensive progress reports | Project Manager |
| Community (Public) | Public forums + website | Quarterly | Project updates, community information | Communications Specialist |
| Media | Press releases + media briefings | As needed | Press releases, media kits | Communications Specialist |

# Communication Types & Protocols

## 1. Internal Communications

### 1.1 Project Team Communications

Daily Stand-ups (Optional):

- Frequency:ly (if needed during critical periods)

- Duration:minutes

- Format:ef status, blockers, priorities

- Owner:ject Manager

- Participants:e project team

- Tools:person, video conference, or collaboration platform

Weekly Team Meetings:

- Frequency:ry Monday (or first working day of week)

- Duration:minutes

- Format:

- Review previous week accomplishments

- Plan current week priorities

- Discuss blockers and risks

- Review budget and timeline

- Owner:ject Manager

- Participants:e project team, working group leads

- Tools:person preferred, video conference acceptable

- Documentation:ting minutes within 24 hours

Working Group Meetings:

- Frequency:kly (each working group)

- Duration:90 minutes

- Format:

- Review work package progress

- Discuss technical issues

- Coordinate with other working groups

- Owner:king Group Lead

- Participants:king group members, subject matter experts

- Documentation:ting notes shared with Project Manager

### 1.2 Steering Committee Communications

Bi-weekly Steering Committee Meetings:

- Frequency:ry two weeks

- Duration:minutes

- Format:

- Executive summary of progress

- Key decisions required

- Risk and issue review

- Budget and timeline status

- Owner:ject Manager

- Participants:ering Committee members

- Documentation:ision log and meeting minutes within 48 hours

Decision Briefs:

- Frequency:needed (minimum 48 hours before decisions required)

- Format:

- Issue/opportunity description

- Options analysis

- Recommendation

- Impact assessment

- Decision required

- Owner:ject Manager

- Distribution:ering Committee members

- Response Time:hours for non-urgent, 24 hours for urgent

### 1.3 Escalation Communications

Issue Escalation:

- Level 1 (Working Group):king group lead addresses within working group

- Level 2 (Project Manager):alate to Project Manager if unresolved in 48 hours

- Level 3 (Steering Committee):alate to Steering Committee if unresolved in 1 week

- Urgent Issues:ediate escalation to appropriate level

- Format:ue log with description, impact, proposed resolution, escalation path

Risk Escalation:

- Low Risk:umented in risk register, reviewed weekly

- Medium Risk:alated to Project Manager, mitigation plan required

- High Risk:alated to Steering Committee immediately, action plan required

- Format:k register update with escalation notification

## 2. External Communications

### 2.1 Government Communications

Provincial Government:

- Frequency:thly progress reports

- Format:mal progress report with metrics, milestones, budget

- Owner:ject Manager

- Distribution:vincial economic development contacts

- Response Protocol:nowledge receipt within 48 hours

Federal Government:

- Frequency:rterly comprehensive reports

- Format:ailed progress report aligned with funding requirements

- Owner:ject Manager

- Distribution:eral funding program contacts

- Response Protocol:nowledge receipt within 1 week

Municipal Government (Town Council):

- Frequency:thly reports to Council

- Format:ncil report format, executive summary

- Owner:

- Distribution:ncil members, public (if required)

- Response Protocol:ncil discussion and feedback

### 2.2 Business Partner Communications

Firefly Metals:

- Frequency:weekly status updates

- Format:

- Status summary

- Requirement confirmations

- Timeline alignment

- Partnership opportunities

- Owner:ject Manager

- Distribution:efly Metals project contacts

- Response Protocol:nowledge within 24 hours, respond to questions within 48 hours

Local Businesses:

- Frequency:thly information sessions

- Format:

- Opportunity updates

- Engagement invitations

- Business development information

- Owner:keholder Coordinator

- Distribution: Chamber of Commerce, business directory

- Response Protocol:P requested, follow-up with non-attendees

### 2.3 Community Communications

Qalipu First Nation:

- Frequency:sultation meetings as required

- Format:

- Consultation materials

- Project updates

- Impact assessments

- Response to concerns

- Owner:keholder Coordinator

- Distribution:ipu First Nation leadership and designated contacts

- Response Protocol:pectful consultation timeline, acknowledge concerns within 1 week

Public Community:

- Frequency:rterly public forums

- Format:

- Public information sessions

- Project updates

- Q&A sessions

- Feedback collection

- Owner:munications Specialist

- Distribution:lic announcements, website, local media

- Response Protocol:ress questions and concerns, follow-up on commitments

Neighboring Communities:

- Frequency:rterly updates

- Format:

- Regional coordination updates

- Opportunity sharing

- Collaboration invitations

- Owner:keholder Coordinator

- Distribution:munity leaders, regional organizations

- Response Protocol:nowledge receipt, respond to inquiries

### 2.4 Media Communications

Press Releases:

- Frequency:or milestones, significant announcements

- Format:ndard press release format

- Owner:munications Specialist

- Distribution:al and provincial media

- Approval:ject Manager and Steering Committee Chair

- Response Protocol:ia inquiries handled within 24 hours

Media Briefings:

- Frequency:needed for major announcements

- Format:ss conference or media briefing

- Owner:munications Specialist

- Participants:ject Manager, Steering Committee Chair, key stakeholders

- Preparation:ia kit, key messages, Q&A preparation

# Communication Tools & Platforms

## Primary Tools

- Email:mary communication channel for formal communications

- Project email: [To be established]

- Distribution lists maintained for stakeholder groups

- Email templates for standard communications

- Project Management Platform: be determined]

- Task tracking

- Document sharing

- Collaboration workspace

- Status updates

- Video Conferencing: remote meetings

- Platform: [To be determined]

- Recording capability for important meetings

- Screen sharing for presentations

- Document Management:tralized document repository

- Version control

- Access permissions

- Document templates

- Website/Portal:lic-facing information

- Project updates

- Public documents

- Event announcements

- Contact information

## Communication Templates

Standard Templates Available:

- Meeting agenda template

- Meeting minutes template

- Status report template

- Decision brief template

- Issue escalation template

- Press release template

- Email templates for common communications

# Communication Schedule

## Weekly Communications

- Monday:kly team meeting

- Tuesday-Friday:king group meetings (scheduled)

- Friday:kly status summary email to Steering Committee

## Bi-weekly Communications

- Week 1:ering Committee meeting

- Week 2:efly Metals status update

- Alternating:king group coordination meetings

## Monthly Communications

- First Week:thly progress report to provincial government

- Second Week:n Council report

- Third Week:al business information session

- Fourth Week:ernal monthly review and planning

## Quarterly Communications

- Quarter End:prehensive progress report to federal government

- Quarter End:lic community forum

- Quarter End:ional community updates

- Quarter End:rterly review and planning session

## As-Needed Communications

- Issue escalations

- Risk notifications

- Media communications

- Consultation meetings

- Decision briefs

- Press releases

# Communication Responsibilities

## Project Manager

- Overall communication coordination

- Steering Committee communications

- Government reporting

- Issue and risk escalation

- Decision briefs

## Stakeholder Coordinator

- Stakeholder engagement communications

- Qalipu First Nation consultation

- Local business communications

- Community engagement

- Regional coordination

## Communications Specialist

- Media relations

- Public communications

- Website/content management

- Press releases

- Public information sessions

## Working Group Leads

- Working group communications

- Technical communications

- Cross-group coordination

- Status updates to Project Manager

## CAO

- Town Council communications

- Municipal government coordination

- Public transparency requirements

# Communication Quality Standards

## Content Standards

- Accuracy: information verified before distribution

- Completeness:munications include necessary context

- Timeliness:ormation shared at appropriate times

- Relevance:ormation tailored to audience needs

- Actionability:ar next steps and responsibilities

## Format Standards

- Consistency:ndard formats across similar communications

- Accessibility:dable by all stakeholders

- Professional:fessional appearance and tone

- Documentation: key communications documented

## Response Standards

- Acknowledgment:eipt acknowledged within 24-48 hours

- Response Time:ponses provided within agreed timeframes

- Follow-up:low-up on commitments and action items

- Escalation:alation when response timeframes not met

# Confidentiality & Information Management

## Confidentiality Levels

- Public:ormation available to all stakeholders and public

- Internal:ormation for project team and working groups

- Confidential:ormation for Steering Committee and key stakeholders

- Restricted:sitive information (financial, legal, strategic)

## Information Sharing Protocols

- Public Information:red through website, public forums, media

- Internal Information:red through project team channels

- Confidential Information:red only with authorized stakeholders

- Restricted Information:red only with explicit authorization

## Document Management

- Version Control: documents versioned and dated

- Access Control:ess permissions based on confidentiality level

- Retention:uments retained per project requirements

- Archival:pleted phase documents archived appropriately

# Communication Review & Improvement

## Review Process

- Quarterly Review:munication effectiveness reviewed quarterly

- Stakeholder Feedback:dback collected on communication quality

- Process Improvement:munication processes refined based on feedback

- Tool Evaluation:munication tools evaluated for effectiveness

## Success Metrics

- Timeliness:munications delivered on schedule

- Response Rates:keholder response and engagement rates

- Satisfaction:keholder satisfaction with communications

- Effectiveness:munication objectives achieved

## Continuous Improvement

- Lessons Learned:munication lessons captured and applied

- Best Practices:t practices identified and shared

- Tool Updates:munication tools updated as needed

- Process Refinement:munication processes refined continuously

# Emergency & Crisis Communications

## Emergency Communication Protocol

- Immediate Notification:ject Manager notified immediately

- Assessment:uation assessed within 1 hour

- Stakeholder Notification: stakeholders notified within 2 hours

- Public Communication:lic communication within 4 hours (if required)

- Ongoing Updates:ular updates until situation resolved

## Crisis Communication Team

- Project Manager:rall coordination

- Communications Specialist:ia and public communications

- Stakeholder Coordinator:keholder notifications

- Steering Committee Chair:ategic decisions

## Crisis Communication Channels

- Internal:ediate team notification

- Stakeholders:ect notification to key stakeholders

- Public:ss release, website update, social media (if applicable)

- Media:ia briefing if required

# Approval & Sign-Off

Document Owner:ject Management Team

Approved By:ering Committee

Date Approved: be completed]

Next Review Date:arterly]

Sign-Off:

- Project Manager:______________ Date: _______

- Steering Committee Chair:______________ Date: _______

- CAO:______________ Date: _______

# Appendices

## Appendix A: Communication Templates

- Meeting agenda template

- Meeting minutes template

- Status report template

- Decision brief template

- Issue escalation template

- Press release template

## Appendix B: Distribution Lists

- Steering Committee distribution list

- Project team distribution list

- Working group distribution lists

- Stakeholder distribution lists

## Appendix C: Communication Tools Setup

- Email setup and distribution lists

- Project management platform configuration

- Document management system setup

- Website/portal setup

## Appendix D: Key Contacts

- Project team contacts

- Stakeholder contacts

- Government contacts

- Media contacts

Document Status:ft - Pending Steering Committee Approval

Version History:

- v1.0 (January 2025): Initial communication protocols document created